## API Changes Needed
# | Date | Screen | File | Endpoint(s) | What's needed | Why | Status
1 | 2026-06-30 | Penpal "All" tab (Discover) | PenpalConnectionsScreen.tsx | GET /penpal/discover | discover response should include a per-user connection status (e.g. connectionStatus: None/Pending/Connected) | Figma "All" tab shows a green Connected badge vs blue Connect per person. Discover currently returns no status. Workaround: client-side merge of discover + getConnections (approximate). | Resolved 2026-08-17
2 | 2026-06-30 | Penpal Public Profile header | PenpalPublicProfileScreen.tsx | GET /penpal/discover GET /penpal/connections GET /penpal/profile | Penpal profile/connection responses should include age (or birthdate) | Figma header shows "Molly1522, 22". No age/birthdate field exists in any penpal type today. | Resolved 2026-08-17
3 | 2026-06-30 | Penpal Public Profile – "Letters Exchanged" | PenpalPublicProfileScreen.tsx | NEW e.g. GET /penpal/letters?withUserId={id} (today: client-side filter of GET /penpal/letters) | (Nice-to-have) a per-penpal conversation endpoint | Figma profile shows the letter thread with one penpal. Achievable client-side by filtering getLetters by counterpart id — no API change strictly required, but a dedicated endpoint would be cleaner/paginated. | Resolved 2026-08-17
4 | 2026-07-02 | Mentor Profile Setup | MentorProfileSetupScreen.tsx | POST /mentor/profile | mentorApi.saveProfile should accept firstName, lastName, title, phone, dateOfBirth, country, city, state, and a profile image. Currently it only takes {displayName, bio, tagline}. | Figma "Ready To Begin?" form collects all those fields. UI now renders them, but only displayName (=first+last), tagline (=title), bio (=about) are submitted; phone / DOB / country / city / state / photo are collected but NOT saved until the endpoint accepts them. | Resolved 2026-08-17
5 | 2026-07-02 | Mentor Subscription price | MentorSubscriptionScreen.tsx | GET /mentor/subscription + store IAP product com.fixit.mentor.monthly | Confirm the real plan price / IAP product. | Figma shows $20/Month; UI now displays $20 (was $9.99). The actual charge is set by the store IAP product (com.fixit.mentor.monthly), not this label — keep them in sync. | Verify
6 | 2026-07-03 | Dating Discover filters | DatingDiscoverScreen.tsx | GET /dating/discover | /dating/discover should accept country, distance, ageMax/ageRange, interestedInGender, interestIds params | Figma has a Filter sheet (country, distance & age sliders, gender, premium Advance Filters). Built the full sheet UI; "Apply" currently only filters the already-loaded page client-side (country + age). Distance can't work at all without server support. | Resolved 2026-08-17
7 | 2026-07-03 | Dating "Likes Received" / "My Likes" tabs | DatingMatchesScreen.tsx | NEW e.g. GET /dating/likes/received GET /dating/likes/sent | Endpoints to list who liked me and who I liked (likes-received gated by premium) | Figma My Matches has 3 tabs. Only GET /dating/matches exists. "Likes Received" shows the locked premium preview; "My Likes" shows an empty state until endpoints exist. | Resolved 2026-08-17
8 | 2026-07-03 | Dating My Profile | DatingMyProfileScreen.tsx | POST /dating/profile GET /users/me (+ login response) for gender | POST /dating/profile should accept pseudoName, dateOfBirth, country, city, state; auth user should expose gender (badge) | Figma profile form collects all of these + a spiritual pseudonym. Today only about / interestedInGender / displayImageId are saved — the rest are collected but NOT submitted. Gallery (upload/delete) works with existing endpoints. | Resolved 2026-08-17
9 | 2026-07-03 | Vetting result | VettingQuizScreen.tsx | POST /dating/vetting/submit | POST /dating/vetting/submit should return eligibility (pass/fail) | Figma has both outcomes: "Congratulations! Your Profile is Approved" (pg 20) and "Sorry! …" + mentors (pg 14). The app currently always shows the Sorry/mentor path because the response isn't consumed. Response shape needs confirming before wiring the approved path. | Open
10 | 2026-07-03 | Dating chat attachments | DatingChatDetailScreen.tsx | POST /api/Dating/matches/{matchId}/upload (EXISTS in Swagger, multipart file) + SignalR delivery | Send image/voice messages — app-side integration of the existing upload endpoint | Swagger check 2026-07-09: the upload endpoint already exists — the app never integrated it. Remaining questions for backend: does upload create/broadcast the chat message (SignalR) or must the client send a follow-up, and is voice (audio/*) accepted? Attach/mic icons are visual-only until wired. | Integrate
11 | 2026-07-03 | Dating Premium | DatingPremiumScreen.tsx | GET/POST/DELETE /dating/subscription/{planType} GET /api/Dating/config (EXISTS, response undocumented) + new store IAP product | Dating IAP product + a daily-swipe-limit signal from the API | Figma: $20/Month premium plan + "You Have Reached Your Daily Limit!" overlay on Discover. Plan card UI is built (status/cancel use existing subscription endpoints); Subscribe shows a "coming soon" alert until the IAP product exists. The daily-limit overlay needs the API to report remaining swipes / a limit error. Swagger check 2026-07-09: GET /api/Dating/config exists and may already expose swipe limits — response schema undocumented; backend to confirm. | Open
12 | 2026-08-17 | Profile images app-wide (seen on My Likes) | DatingMatchesScreen.tsx | Static hosting for profileImageUrl paths e.g. /profiles/{userId}/{guid}.png | Uploaded profile images are not reachable. Serve the stored paths (or return absolute URLs). | Likes response returns "profileImageUrl": "/profiles/90/3e3859dd-….png". The app resolves relative paths against the API origin, but that URL 404s — verified against https://beta.contentdevelopmentpros.com:4125 and the /api, /uploads, /files, /media, /images, /static, /wwwroot prefixes plus the port-443 host. Either static file middleware isn't configured for /profiles, the file was never written, or images live on another host. Client-side URL handling is correct; cards now fall back to initials. | Open
13 | 2026-08-17 | Dating Profile Detail opened from Likes | DatingProfileDetailScreen.tsx | NEW e.g. GET /dating/users/{userId} or add about/interests/images/iceBreakerQuestions to the likes endpoints | A way to fetch another user's full dating profile by id | The Figma profile detail shows About, Interest chips and the Gallery grid. Discover carries those fields so the screen is complete when opened from swiping, but the likes rows only return summary fields — opening a profile from My Likes / Likes Received renders header-only and those sections are hidden. No "get another user's profile" endpoint exists in Swagger today. | Open